Managing ECML projects

- The project team

    - Roles

    - Tasks

    - Fees

- Project activities

http://www.ecml.at/Projectmanagement

The project team

| √ Roles | √ Tasks | √ Annual fees |
| --- | --- | --- |
| Coordinator | - regular liaison with the ECML Secretariat on all project-related matters - responsible for all matters related to project content - leading the project team and coordinating the project - implementing the agreed action plan to the agreed standards and deadlines - ensuring the effective preparation and delivery of all project events and meetings and production of all necessary documentation - taking responsibility for the effective flow of information between team members, participants in project activities, and the ECML - ongoing evaluation of project activity and reporting on project progress to the ECML - submission of the final results of the project to the ECML - submitting the project description in the second working language - submitting an initial bilingual project glossary in the template provided by the ECML covering about 10 key terms of the project topic in the two working languages | €2400 |
| Website correspondent | - Responsible for internal and public project website concerning - Regular updating of news, documents, calendar, - Moderating the website (forum, chat); responding to questions from the team and giving advice on technical/administrative issues with the support of the ECML webmaster - providing texts and materials for regular updating of the project website in order to inform the wider public about the project and attract the interest of the targeted audience. | €700 |
| Second working language documentalist | - Responsible for documentation of major working documents in the second working language - Responsible for the elaboration of the project glossary - Overseeing the project website in the second working language - Liaising with the ECML concerning questions with regard to the second working language | €700 |
| Mediation link person | - communicate with teams of selected ECML projects related to their own project ; - communicate relevant information to the wider audience (e.g. sending project news to relevant networks, webmasters, newsletter editors); - participate in meetings of ECML projects which have been identified as related to their own project, at their instigation and upon request to the Centre. | €700 |

Project activities financed by the European Centre for Modern Languages

For detailed information on tasks related to individual activities, please go to 	http://www.ecml.at/Projectmanagement

| Activity format | Days | Venue | Interpretation between working languages provided by ECML | Travel and subsistence provided by ECML | Complementary information |
| --- | --- | --- | --- | --- | --- |
| Expert meeting (EX) | 2 | ECML, Graz | No | 4 team members |  |
| Workshop (WS) | 2-4 | ECML, Graz | Yes, for plenary sessions | - 4 team members & - 32 nominated participants from ECML member states* | Preceded by a preparatory meeting (1 day) for the team in Graz |
| Network meeting (NW) | 2 | ECML, Graz | No | - 4 team members & - max of 16 participants | Preceded by a preparatory meeting (1 day) for the team in Graz |
| Regional workshop (RW) | 2-3 | Host institution in ECML member state | No | - 4 team members (as moderators of the event) & - max of 6 invited participants from ECML member states | - participation of an ECML staff member presenting the work of the ECML at the beginning of the event - preceded by a preparatory meeting (1 day) for the moderators and the ECML staff member - 1 local coordinator (contract with ECML covering fee of €230) & - local experts invited by host institution |
| National event (NE) | 1-2 | Host institution in ECML member state | No | - 2 team members (as moderators of the event) | - 1 local coordinator (contract with ECML covering fee of €230) & - local participants invited by host institution |

* The team may recommend participants to be nominated by ECML member states.