[image: image1.jpg]"2%E EMPOWERING LANGUAGE |
= VALORISER LES PROFESSIONNEL

SPRACHLEHREN!m“’ gt ECML-CELV-EFSZ

2008-2011





2009 Annual plan and annual report 

FROM ECML project coordinator
	Project title and acronym
	LACS: Language Associations and Collaborative Support

	Coordinator
	Terry Lamb

	Project team members
	Sigurborg Jonsdottir, Lucka Pristavec, Janina Zielinska; associate partner: Nicole Thibault

	Programme consultant
	Frank Heyworth


	Annual Project Plan 

To be filled in, discussed with your programme consultant and submitted 

to the ECML by 15 January 2009
	Annual Project Report

To be filled in and submitted to the ECML 

by 20 November 2009

	Report from:

Project coordinator
Addressee(s):

The ECML Secretariat
	Purpose
	Reference and reporting format
	Report from:

Project coordinator

Addressee(s):

The ECML Secretariat and the programme consultant
	Purpose
	Reference and reporting format

	
	To produce an agreed annual plan for the project, stating the desired outcome of the year’s work, what the activities will be, what different outputs are to be produced, how the work will be evaluated at the end of the year.
	The basic reference documents for this plan are:

· the framework for ECML programme evaluation;

· The reporting procedures for the ECML programme 2008 – 2011; 

· the project description submitted to the ECML in 2 languages.


	
	To produce an annual report for the project, as material for the ECML’s report to its Governing Board. It is based on the annual project plan.
	The report is based on the annual plan as well as on the project description. Submission of the annual report 2008 together with the annual plan for 2009.


For terminology please see “Framework for ECML programme evaluation”: http://coordination.ecml.at/Portals/3/documents/refdocs/01_Framework%20for%20ECML%20programme%20evaluation_rev.doc 

	Item 1

What do you plan to have achieved by the end of the year (in relation to the project outcomes / project aim; C5 in the project description)?
	Annual report on item 1

	1. To have further increased awareness amongst all FIPLV/FIPF/IDV member associations of progress with the LACS project and of the ECML programme, e.g. through an article for newsletters, through weblinks, and through the FIPLV World Congress in June-July 2009. Also to consider barriers, e.g. a strategy for bringing ECML work to the fore in national conference planning as well as more localised activity.

2. To have added further to our knowledge base regarding language teacher association organisation and activity (dissemination activities and impact on policy). This will be achieved by further distribution of the questionnaire, analysis of member association reports, discussions/interviews at FIPLV World Congress, and ECML Workshop activities. The intention is to support the member associations in building and retaining membership, in supporting their members, in disseminating innovative policy and practice, and in influencing policy.

3. To continue to explore the notion of dissemination itself, and associated opportunities, challenges and solutions. This includes the issue of collaboration with other associations\organisations as well as innovation in the use of new technologies. Discussions will take place at planned meetings of FIPLV and at the ECML Workshop, and will use ECML projects as case study materials. Relevant materials/articles on dissemination itself will be sourced and used.

4. To develop a draft of a 'how to' manual, and to explore the most effective ways of making this accessible to member assocations.

5. To consider ways in which collaboration across language teacher associations can best be achieved using existing networks and new technologies.

6. To identify relevant member association journals and produce a strategy for encouraging ECML project members to publish in them


	


	Item 2 

What outputs will be produced during the year (in relation to the specific objectives of the project; C5 in the project description)?
	Annual report on item 2

	1. An update report will be produced with further information about ECML projects, placed on the website, and sent to all member associations with a request for it to be circulated in paper and electronic newsletters.

2. The survey outcomes will be enhanced through further circulation of the questionnaire, and the analysis will be updated.

3. A Workshop programme and report will be produced, addressing issues such as: role of FIPLV/FIPF/IDV/ECML in supporting language teacher associations; ideas on dissemination, using ECML project outcomes; ways of evaluating impact.

4. An initial draft of a ‘how to’ manual will be produced.

5. Website development will be given priority, considering synergies with FIPLV and other websites.

6. Where appropriate, publication of activities will be considered and planned, e.g. in the proceedings of the FIPLV World Congress, in targeted member association journals, and in the International Journal of Innovation in Language Learning and Teaching.


	     


	Item 3

What activities are planned for the year?
	Annual report on item 3

	1. Expert meeting (April 2009). 

2. Meetings of the FIPLV Executive Committee and World Council in Moscow (not funded by ECML) (June-July 2009).

3. FIPLV World Congress (not funded by ECML) (July 2009).

4. Workshop (December 2009).


	     



	Item 4

How will you use your project website (forums, chats, resources etc.)?
	Annual report on item 4

	Links between LACS and other websites will be reviewed

Relevant resources will be added, e.g. survey outcomes

Involvement of member associations in population of the website will be encouraged (statutes; newsletters; activities; resources; project links, etc) and synergies with FIPLV website will be considered

Ways of highlighting specific ECML projects will be considered

Use of the website for pre-workshop activity will be discussed




	     


	Item 5

What activities are planned this year for disseminating the work of the project to the stakeholders for whom the project is designed (in relation to the project dissemination plan; D4 in the project management plan)?
	Annual report on item 5

	website development

newsletter article to update on the project, for distribution to member associations

identification of member association journals and encouragement of ECML project members to publish in them
FIPLV World Congress in Moscow

Workshop in December, and consideration of member association dissemination at national levels


	


	Item 6

List the indicators of achievement that will enable the success of the year’s work to be evaluated (in relation to the evaluation plan of the project (D3 in the project management plan).
	Annual report on item 6

	Expert meeting evaluations

Population of the website

Additional questionnaire responses

Workshop evaluations

Articles published in member association newsletters

Articles submitted to journals

Post-Workshop plans for dissemination by member associations

Dissemination activity at FIPLV World Congress

Draft content of 'how to' manual


	



	Item 7

Are there any special resources / support you would like from the ECML?
	Annual report on item 7

	No

	     


	Date completed : 17 April 2009
	

	Item 8
Consultation of programme consultant


	What is your overall evaluation of this year’s work in the project? Mention any particular achievements which it would be important to refer to in the ECML’s annual report.

	Seen by the project consultant /

Project consultant’s comments have been taken into account  FORMCHECKBOX 

(to be ticked by project coordinator)

	     

	Date completed : 17 April 2009
	Date completed :      
Please write a news item on project achievements in the year 2009 and post it on your project website in the two/three working languages 
by 10 December 2009.











[image: image2.jpg]E G M Q European Centre for Modern Languages
iy 'ty Centre européen pour les langues vivantes
L

E m COUNCIL  CONSEIL

OF EUROPE __DE L'EUROPE






