[image: image1.jpg]"2%E EMPOWERING LANGUAGE |
= VALORISER LES PROFESSIONNEL

SPRACHLEHREN!m“’ gt ECML-CELV-EFSZ

2008-2011





2008 Annual plan and annual report 

FROM ECML project coordinators 
	Project title and acronym
	LACS: Language Associations and Collaborative Support

	Coordinator
	Terry Lamb

	Project team members
	Sigurborg Jonsdottir, Lucka Pristavec, Janina Zielinska; associate partner: Nicole Thibault

	Programme consultant
	Frank Heyworth


	Annual Project Plan 

To be filled in, discussed with your programme consultant and submitted 

to the ECML by 31 January 2008
	Annual Project Report

To be filled in and submitted to the ECML 

by 30 November 2008

	Report from:

Project coordinator
Addressee(s):

The ECML Secretariat
	Purpose
	Reference and reporting format
	Report from:

Project coordinator

Addressee(s):

The ECML Secretariat and the programme consultant
	Purpose
	Reference and reporting format

	
	To produce an agreed annual plan for the project, stating the desired outcome of the year’s work, what the activities will be, what different outputs are to be produced, how the work will be evaluated at the end of the year.
	The basic reference documents for this plan are:

· the framework for ECML programme evaluation;

· The reporting procedures for the ECML programme 2008 – 2011; 

· the project description submitted to the ECML in 2 languages.


	
	To produce an annual report for the project, as material for the ECML’s report to its Governing Board. It is based on the annual project plan.
	The report is based on the annual plan as well as on the project description. Submission of the annual report 2008 together with the annual plan for 2009.


For terminology please see “Framework for ECML programme evaluation”: http://coordination.ecml.at/Portals/3/documents/Evaluation_Approach.doc 

	Item 1

What do you plan to have achieved by the end of the year (in relation to the project outcomes / project aim; C5 in the project description)?
	Annual report on item 1

	1. To have disseminated the overall programmes (previous and current) of ECML projects to FIPLV members attending planned meetings, and at the AILA World Congress.
2. To conduct an initial mapping activity (through a questionnaire) with regard to the ways in which language teacher associations (unilingual and multilingual) are organised (nationally, regionally and locally) in order to support their own networks of members through practical interventions (workshops, publications, newsletters, websites and web fora etc) as well as through opportunities to influence policy.
3. At planned meetings of FIPLV, to begin to explore the notion of dissemination itself, and associated opportunities, challenges and solutions. This includes the issue of collaboration with other associations\organisations as well as innovation in the use of new technologies.


	     


	Item 2 

What outputs will be produced during the year (in relation to the specific objectives of the project; C5 in the project description)?
	Annual report on item 2

	1. Questionnaire (in three languages) for mapping language teacher association structure and activities.

2. Presentation of the initial mapping (Powerpoint presentations).

3. Relevant sections of notes from planned meetings.
4. Appropriate weblinks from and to LACS and ECML.


	     


	Item 3

What activities are planned for the year?
	Annual report on item 3

	1. Expert meeting (April 2008) 

2. Meetings of the FIPLV Executive Committee and World Council (not funded by ECML) (April 2008).

3. Attendance at the AILA World Congress (not funded by ECML) (August 2008).

4. Attendance at the workshop for National Contact Points (September 2008).


	     



	Item 4

How will you use your project website (forums, chats, resources etc.)?
	Annual report on item 4

	1. To upload the products developed in 2008 in order to provide information on project developments.

	     


	Item 5

What activities are planned this year for disseminating the work of the project to the stakeholders for whom the project is designed (in relation to the project dissemination plan; D4 in the project management plan)?
	Annual report on item 5

	All of the activities in items 3, 4 and 5 above.

	     


	Item 6

List the indicators of achievement that will enable the success of the year’s work to be evaluated (in relation to the evaluation plan of the project (D3 in the project management plan).
	Annual report on item 6

	1. Greater awareness of ECML activities amongst those attending the above events.

2. The number and quality of returns to the questionnaire survey.

3. Comments and questions arising from the AILA World Congress presentation.

4. Quality of the project website.


	     



	Item 7

Are there any special resources / support you would like from the ECML?
	Annual report on item 7

	  No.   



	     


	Date completed :      
	

	Item 8
Programme consultant’s comment


	What is your overall evaluation of this year’s work in the project? Mention any particular achievements which it would be important to refer to in the ECML’s annual report.

	     
Date completed :      
	Write a brief news item as the annual project bulletin for your public project website

	Comment of consultant has been taken into account

Revised version completed :      
	Date completed :      











[image: image2.jpg]E G M Q European Centre for Modern Languages
iy 'ty Centre européen pour les langues vivantes
L

E m COUNCIL  CONSEIL

OF EUROPE __DE L'EUROPE






